## Sheet1
Task | Section | Estimated Complexity | Estimated Deadline | Actual Completion Date
ConstructionMaterial Class | INVENTORY | LOW | 2019-10-07 | 2019-10-02
Entry Class | INVENTORY | LOW | 2019-10-07 | 2019-10-02
Inventory list | INVENTORY | LOW | 2019-10-07 | 2019-10-02
Placement at mouse | ASSEMBLY | LOW | 2019-10-07 | 2019-10-07
Raycast layers for each material | ASSEMBLY | LOW | 2019-10-07 | 2019-10-07
Example completed build | ASSEMBLY | LOW | 2019-10-07 | 2019-10-07
Snap grid | ASSEMBLY | LOW | 2019-10-07 | 2019-10-07
Shop UI | SHOP | LOW | 2019-10-21 | 2019-10-21
Get inputs from UI | SHOP | LOW | 2019-10-21 | 2019-10-21
Add shop purchases to inventory | SHOP | LOW | 2019-10-21 | 2019-10-21
Reset input fields on close | SHOP | LOW | 2019-10-21 | 2019-10-21
Special snapping for stringers | ASSEMBLY | MEDIUM | 2019-10-14 | 2019-10-09
Camera movement | ASSEMBLY | LOW | 2019-10-14 | 2019-10-07
Overall timer | ASSEMBLY | LOW | 2019-10-28 | 2019-10-23
Pause Screen | ASSEMBLY | LOW | 2019-10-28 | 2019-10-23
Layer selection and recording | ASSEMBLY | MEDIUM | 2019-10-28 | 2019-10-23
Recording extra shopping visits | ASSEMBLY | LOW | 2019-10-28 | 2019-10-21
Displayed inventory | ASSEMBLY | MEDIUM | 2019-10-28 | 2019-10-02
Useable inventory for selection | ASSEMBLY | LOW | 2019-10-28 | 2019-10-02
Cutting UI | CUT | MEDIUM | 2019-11-18 | 2019-10-30
Cutting material verification | CUT | MEDIUM | 2019-11-18 | 2019-11-11
Cutting waste calculation | CUT | MEDIUM | 2019-11-18 | 2019-11-11
Change inventory | CUT | HARD | 2019-11-18 | 2019-11-11
Resize and reposition materials | CUT | MEDIUM | 2019-11-18 | 2019-10-28
Quantity score | GRADING | LOW | 2019-11-22 | 2019-11-11
Cutting score | GRADING | LOW | 2019-11-22 | 2019-11-13
Placement score | GRADING | MEDIUM | 2019-11-22 | 2019-11-13
Results screen | GRADING | LOW | 2019-11-22 | 2019-11-13